## Wed 7-18
TUNE Postback 18 Production Schedule - Version 3
Wednesday July 18th |  | TUNE Postback/McCaw Hall
Time | Task | Notes
6am | Call Time
6 - 10am | TPN: Meaghan (Project Manager) arrive Aaron (Technical Manager) arrive Deliveries: Scenic Walls, Carpet, TUNE letters AVMS: Load in Screen & Projector Content Machines McCaw Hall: Audio Lighting (with TPN's LD)
7am | Work continues Deliveries Stage furniture - Proper Planning Scenic Elements: Assemble TUNE letters Prep hanging scenic pieces
10 - 11am | Lighting: Focus Spike furniture: - couch, 2 chairs, coffee table - 2 chairs, no couch or coffee table - podium? Seat Covers: - cover the back 3 rows on house right and house left sections (100 seats)
11am - 12pm | Lunch - walk away, 1 hour
12pm | All departments continue. Stage Manager arrives
2pm | Tech and test IMAG
4-5pm | Break, 1 hour.
5 - 6:30pm | Rehearse Opening Number: Peter, singers, piano
6:30 - 7:30pm | Rehearse Keynote: Peter (with ppt clicker and notes monitor)
7:30pm - 8:30pm | Record VOG with Peter (off stage) … 1. [5 min before start] Ladies and Gentleman, our program will begin in 5 minutes. 2. [3 min before start] Ladies and Gentleman, please take your seats the program will begin shortly. 3. [1 min before start] Ladies and Gentleman, please take your seats the program is about to begin. Emcee Rehearse (tentative): test mic, walk stage, practice enter/exit Cue to Cue with Ciara: See all the slides, hear stingers, see lighting levels & looks
8:30 - 9pm | Continue Tech and any Updates/Changes Meet about plan for Thursday morning.
9pm | Call Ends
Need at least 9 hour turnaround minimum

## Thurs 7-19
TUNE Postback 18 Production Schedule - Version 3
Thursday July 20 |  | TUNE Postback/McCaw Hall
Time | Task | Labor
7:30am | Call Time
7:30am - 8:30am | Additional Tech
8:30 - 9am | Tentative - speaker practice/walk stage
9am | Doors Open
9:30am | Morning Program begins
12:30pm | Morning Program concludes
12:30 - 1:10pm | Lunch (provided)
1:15pm | Crew back in place
1:15pm | Doors
1:30pm | Afternoon Program begins
5:00pm | Afternoon Program concludes
5:00 - 5:15pm | Short Break.
5:15 - 5:30pm | Any rehearsal for Friday? Review plan for tomorrow.
6pm | Call Ends

## Fri 7-20
TUNE Postback 18 Production Schedule - Version 3
Friday July 21 |  | TUNE Postback/McCaw Hall
Time | Task | Labor
8:00am | Call Time
8:00 - 9:00AM | Additional Practice. Cover 300 seats (back 7 rows on left and right side of auditorium, and back 6 rows in the center).
9 - 9:30am | Tentative - speaker practice/walk stage
9:30am | Doors Open
10:00am | Morning Program begins
12:15pm | Morning Program concludes
12:15 - 1:15pm | Lunch (provided)
1:15pm | Crew in place. Doors Open.
1:30pm | Afternoon program begins
3:45pm | Afternoon program concludes
4:00pm | (when last guest leaves) Doors close
4:00pm | Begin strike
4:30pm | Pick Ups: TPN - scenic, carpet Proper Planning - furniture, 3D letters AVMS - load truck
7:30pm | Call ends. Do we need to add a break? Last year we were able to avoid it.