## Sheet1
S. No. | Task | Estimates Given | Hours Consumed | Hours Balance | Comments
1 | Project Setup + Yii Setup+ Database setup | 12 | 8 | 4 | 4 hour Will be consumed in next milestone for database changes
2 | Theme Customization | 45 | 6 | 39 | 39 hours will be consumed in next milestones pages design implementation
3 | M1 > Register | 6 | 4 | 2 | 2 hours will consumed in validation implementation
4 | M1> Login/Logout | 4 | 4 | 0
5 | M1 > Forgot Password | 1 | 1 | 0
6 | M1 > Top Header UI + Functionality | 22 | 4 | 18 | 18 hours will consumed in functionality implementation of search + dropdown + notification
7 | M1 > Landing Page Menu Area | 12 | 8 | 4 | 4 hours will consumed in next milestones for menu linking
8 | M2> Current Project Listing | 4 | 2 | 2 | 2 hours will consumed in next tasks of current milestone
9 | M2> Create New Project | 32 | 20 | 12 | 12 hours will consumed in validations implementation + linking with add client + linking with contact
| Total | 138 | 57 | 81